## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
First Milestone : Tablet Preparation
Researching tablet features | Optimistic : The tablet has all desired features, Most Likely: The tablet most likely has several features that are needed, Pessimistic : The tablet doesn't have any feature at all, need customization by ourself |  |  | seven days
Comparing tablet pricing | Optimistic : The tablet pricing has reasonable pricing; lead to less-finding tablet, Most Likely : The tables pricing has pretty bearable pricing; lead to more-time finding or compromise, Pessimistic: The tablet pricing cost too much; leading to unscope budget from initial agreement in project proposal and lead to more-time finding much longer with worst case to compromise the cost causing budget adjustment |  |  | seven days
Decide OS for Tablet | Optimistic : There is certain amount of operating system that compatible with software requirements leading to less-time effort to find the suitable os/software, Most Likely: there is several amount of operating system that are compatible with several software requirements leading to more-time effort for finding the suitable os/software, Pessimistic: there isn't any operating system nor software leading to much more-time effort for finding the desired tablet |  |  | three days
Decide tablet vendor | Optimistic : There is vendor which provided the right tablet, Most-Likely : There are several vendor which provided the right tablet, Pessimistic : There is no vendor which provided the right tablet (Right means the tablet has specification based on agreement in project propo and project charter) |  |  | seven days
Shipping and receiving |  |  |  | seven days
Second Milestone : Rollout Preparation
Schedule an electrician |  |  |  | three days
Finalizing the Menu Contents |  |  |  | seven days
FInalizing the Design Mock-ups |  |  |  | seven days
Uploading the Contents |  |  |  | one day
Checking POS System Version |  |  |  | one day
Updating POS System Version |  |  |  | four days
Quality test tablet |  |  |  | one day
Setting up the Tablet for customization and branding |  |  |  | seven days
Initial running the tablet |  |  |  | one day
Third Milestone : Conducting Training
Preparations and planning |  |  |  | one week
Specific training for all Manager |  |  |  | one day
run the staff through some training |  |  |  | one day
Fourth Milestone : First Initial Tablet Test |  |  |  | one day
Fiveth Milestone : First Initial Tablet Rollout |  |  |  | one day
Sixth Milestone : Launching day |  |  |  | one day

## Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
First Milestone : Tablet Preparation
Researching tablet features | Optimistic : The tablet has all desired features, Most Likely: The tablet most likely has several features that are needed, Pessimistic : The tablet doesn't have any feature at all, need customization by ourself | seven days | two days | four days | seven days | H
Comparing tablet pricing | Optimistic : The tablet pricing has reasonable pricing; lead to less-finding tablet, Most Likely : The tables pricing has pretty bearable pricing; lead to more-time finding or compromise, Pessimistic: The tablet pricing cost too much; leading to unscope budget from initial agreement in project proposal and lead to more-time finding much longer with worst case to compromise the cost causing budget adjustment | seven days | one day | three days | seven days | H
Decide OS for Tablet | Optimistic : There is certain amount of operating system that compatible with software requirements leading to less-time effort to find the suitable os/software, Most Likely: there is several amount of operating system that are compatible with several software requirements leading to more-time effort for finding the suitable os/software, Pessimistic: there isn't any operating system nor software leading to much more-time effort for finding the desired tablet | three days | two hours | one day | three days | H
Decide tablet vendor | Optimistic : There is vendor which provided the right tablet, Most-Likely : There are several vendor which provided the right tablet, Pessimistic : There is no vendor which provided the right tablet (Right means the tablet has specification based on agreement in project propo and project charter) | seven days | one day | three days | seven days | H
Shipping and receiving |  | seven days |  |  |  | H
Second Milestone : Rollout Preparation
Schedule an electrician |  | three days |  |  |  | H
Finalizing the Menu Contents |  | seven days |  |  |  | H
FInalizing the Design Mock-ups |  | seven days |  |  |  | H
Uploading the Contents |  | one day |  |  |  | H
Checking POS System Version |  | one day |  |  |  | H
Updating POS System Version |  | four days |  |  |  | H
Quality test tablet |  | one day |  |  |  | H
Setting up the Tablet for customization and branding |  | seven days |  |  |  | H
Initial running the tablet |  | one day |  |  |  | H
Third Milestone : Conducting Training
Preparations and planning |  | one week |  |  |  | H
Specific training for all Manager |  | one day |  |  |  | H
run the staff through some training |  | one day |  |  |  | H
Fourth Milestone : First Initial Tablet Test |  | one day |  |  |  | H
Fiveth Milestone : First Initial Tablet Rollout |  | one day |  |  |  | H
Sixth Milestone : Launching day |  | one day |  |  |  | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customers would be satisfied by a faster, more efficient experience | Good average ticket time with eight minutes for appetizers and 12-15 minutes for entrees | Is customer average ticket time too long? | Types of orders, number of minutes ticket time | FALSE
| one-minute checkout time and ensure the checkout process is seamless and easy to navigate |  |  | FALSE
| Less than 5% of customers who use the tablets to report technical issues each week | Is there any problems about the tablet that we need to address for the customer? | Number of reports | FALSE
| Aim for 98% order accuracy | How customer think about the accuracy order? Is there any problem we should know about the order accuracy using the tablet? | Number of order that perfectly accurate when using the tablet | FALSE
| Decreased customer wait time in the lobby, average wait time of ten minutes or less before customers are seated. |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Good average ticket time with eight minutes for appetizers and 12-15 minutes for entrees | Is customer average ticket time too long? | Types of orders, number of minutes ticket time | Have you ever visited the Sauce And Spoon Restaurant before? | Yes/No | Yes | No
one-minute checkout time and ensure the checkout process is seamless and easy to navigate |  |  | How long does it take the average ticket time you ever experienced in this restaurant? | Open-ended | Open-ended
Less than 5% of customers who use the tablets to report technical issues each week | Is there any problems about the tablet that we need to address for the customer? | Number of reports | Have you used our new tablet technology for ordering from the menus? | Yes/No | Yes | No
Aim for 98% order accuracy | How customer think about the accuracy order? Is there any problem we should know about the order accuracy using the tablet? | Number of order that perfectly accurate when using the tablet | What is your experience when using the rollout tablet? | Open-ended | Open-ended
Decreased customer wait time in the lobby, average wait time of ten minutes or less before customers are seated. |  |  | Please remark this statement with True or False (T/F) : The Rollout tablet makes my experience for ordering menus more easy and more seamless | True/False | True | FALSE
|  |  | Please remark this statement with True or False (T/F) : The Rollout Tablet makes my ordering process more accurate | True/False | True | FALSE
|  |  | How would you rate your overall experience when using The Rollout Tablet? (Scale from one to five) | Scaled | 1 | 2 | 3 | 4 | 5
|  |  | The following options are the most important features in The Rollout Tablet | Multiple choice | The Rollout Tablet must have easy navigation for the customer | The Rollout Tablet must provided with live-tutorial at the screen of Tablet | The Rollout Tablet must have provided with variety of discount to attract the customer to use it | The Rollout Tablet mustintegrated correctly with the system when ordering the food to avoid misordering | All the options
|  |  | Any suggestion or recommendation about the new rollout system? Please provided it below | Open-ended | Open-ended